## Project Spend Assumptions (3)
Sub Business Line | Cost Line | Spend Type | Spend Sub Category | Cost (Budget) | Open PO Value | Invoiced Actual | Comments
WIS | M&S | Operational | Coil Strings | 490

## Project Spend Assumptions (2)
Sub Business Line | Cost Line | Spend Type | Spend Sub Category | Cost (Budget) | Actual | Comments
WIS | M&S | Operational | Coil Strings | 490
WIS | M&S | Operational | Coil Drums | 370
WIS | M&S | Operational | Coil Monocable | 120
WIS | M&S | Operational | ACTive | 350
WIS | M&S | Operational | PCE 7in Risers | 250
WIS | M&S | Maintenance | BOP Recert / Spares | 100
WIS | M&S | Maintenance | Treating Iron | 100
WIS | M&S | Operational | IH Stand for Stabbing | 150 |  | Local or Singapore?
WIS | M&S | Operational | PCE X-Overs / Lifting Caps | 80
WIS | M&S | Maintenance | Maintenance Recert | 150
WIS | M&S | Operational | Critical Ops Spare Parts | 150 |  | Highly uncertain, could be up to 300k
TCP | M&S | Operational | CIRP Stack Frame | 150
TCP | M&S | Operational | CIRP M&S | 900

## Project Spend Assumptions
Sub Business Line | Spend Type | Initial Cost Assumption Jun 2024 | Updated Cost Assumption Jan 2025 | Updated Cost Assumption Mar 2025 | Invoiced As of Today | Open PO Value | Comments
CT | Coil Strings | 350 | 490 | 490 | 514 | 0 | Two strings to be ordered
CT | Coil Drums | 350 | 360 | 370 |  | 370
CT | ACTive M&S | 150 | 350 | 350 | 302
TCP | CIRP M&S | 500 | 600 | 900 | 300 | 200

## PO Mapping Inbox
PO Number | Vendor Name | Total Value (USD) | PO Line Item | Part Number | Description | Quantity | UoM | PO Creation Date | Location | FMT PO | Invoiced Quantity | Invoiced Value (USD) | Invoice Date
4584165035 | SPOOLTECH, LLC. | 340536.18 | 1 | 105935866 | 180" x 112" x 96" OD SPL PCK | 2 | EA | 2025-06-05 | Jandakot | No | 1 | 170268.09 | 2025-07-15
4584387743 | Houston Hub | 2334.5 | 13 | 103625685 | KIT, EXPORT,1502 UNION - MALE - 2.875 IN | 1 | EA | 2025-08-27 | Jandakot | No | 1 | 2334.5 | 2025-08-25
4584387743 | Houston Hub | 8113 | 11 | 103463958 | TUBING, COIL, CONT, DURACOIL 130, 2.375 | 700 | FT | 2025-08-27 | Jandakot | No | 700 | 8113 | 2025-08-25
4584387743 | Houston Hub | 7400 | 10 | 103451661 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 800 | FT | 2025-08-27 | Jandakot | No | 800 | 7400 | 2025-08-25
4584387743 | Houston Hub | 6816 | 8 | 103451662 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 800 | FT | 2025-08-27 | Jandakot | No | 800 | 6816 | 2025-08-25
4584387743 | Houston Hub | 7760 | 7 | 103451663 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 1000 | FT | 2025-08-27 | Jandakot | No | 1000 | 7760 | 2025-08-25
4584387743 | Houston Hub | 8830 | 9 | 103451665 | TUBING, MONO, DURACOIL 130, 2.375 IN, .1 | 1000 | FT | 2025-08-27 | Jandakot | No | 1000 | 8830 | 2025-08-25
4584387743 | Houston Hub | 54832 | 6 | 103451667 | TUBING, MONO, DURACOIL 130, 2.375 IN, .1 | 7450 | FT | 2025-08-27 | Jandakot | No | 7450 | 54832 | 2025-08-25
4584387743 | Houston Hub | 73017 | 12 | 103103801 | TUBING, STRAIGHT WALL, 130, 2.375 IN, 0~ | 6300 | FT | 2025-08-27 | Jandakot | No | 6300 | 73017 | 2025-08-25
4584412814 | Houston Hub | 2300 | 13 | 103625685 | KIT, EXPORT,1502 UNION - MALE - 2.875 IN | 1 | EA | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 7994 | 12 | 103463958 | TUBING, COIL, CONT, DURACOIL 130, 2.375 | 700 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 7650 | 9 | 103451663 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 1000 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 6712 | 8 | 103451662 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 800 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 7288 | 7 | 103451661 | TUBING, CONT, DURACOIL 130, 2.375 IN, .1 | 800 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 54012.5 | 11 | 103451667 | TUBING, MONO, DURACOIL 130, 2.375 IN, .1 | 7450 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 8700 | 10 | 103451665 | TUBING, MONO, DURACOIL 130, 2.375 IN, .1 | 1000 | FT | 2025-09-05 | Jandakot | No
4584412814 | Houston Hub | 71946 | 6 | 103103801 | TUBING, STRAIGHT WALL, 130, 2.375 IN, 0~ | 6300 | FT | 2025-09-05 | Jandakot | No