## Project Spend Assumptions (3)
Sub Business Line | Cost Line | Spend Type | Spend Sub Category | Cost (Budget) | Open PO Value | Invoiced Actual | Comments
WIS | M&S | Operational | Coil Strings | 490

## Project Spend Assumptions (2)
Sub Business Line | Cost Line | Spend Type | Spend Sub Category | Cost (Budget) | Actual | Comments
WIS | M&S | Operational | Coil Strings | 490
WIS | M&S | Operational | Coil Drums | 370
WIS | M&S | Operational | Coil Monocable | 120
WIS | M&S | Operational | ACTive | 350
WIS | M&S | Operational | PCE 7in Risers | 250
WIS | M&S | Maintenance | BOP Recert / Spares | 100
WIS | M&S | Maintenance | Treating Iron | 100
WIS | M&S | Operational | IH Stand for Stabbing | 150 |  | Local or Singapore?
WIS | M&S | Operational | PCE X-Overs / Lifting Caps | 80
WIS | M&S | Maintenance | Maintenance Recert | 150
WIS | M&S | Operational | Critical Ops Spare Parts | 150 |  | Highly uncertain, could be up to 300k
TCP | M&S | Operational | CIRP Stack Frame | 150
TCP | M&S | Operational | CIRP M&S | 900

## Project Spend Assumptions
Sub Business Line | Spend Type | Initial Cost Assumption Jun 2024 | Updated Cost Assumption Jan 2025 | Updated Cost Assumption Mar 2025 | Invoiced As of Today | Open PO Value | Comments
CT | Coil Strings | 350 | 490 | 490 | 514 | 0 | Two strings to be ordered
CT | Coil Drums | 350 | 360 | 370 |  | 370
CT | ACTive M&S | 150 | 350 | 350 | 302
TCP | CIRP M&S | 500 | 600 | 900 | 300 | 200

## PO Mapping Inbox
PO Number | Cost Line | Project | Sub Business Line | Plant | Net Order Value in USD | Purchase Requisition Number | Purchase Requisition Number : created by (Text) | Purchase Requisition: Creation Indicator (Text) | SLB Vendor Category | Main Vendor name
| Valuation Class | WBS
G/L Account